## Sheet1
Plan For Carmax Data Comp
Group : Carmax Fan Club
Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3
2020-01-26 | 2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 | 2020-02-01 | 2020-02-02 | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08 | 2020-02-09 | 2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13
research what makes |  | Go over what data |  | Collect and clean data |  | Base what we know | Translate model ideas |  |  | Work towards improving what we have |  |  |  | Design and work on |  | Review errors create |  | Final day
customers loyal |  | we have and where we |  | from all sources |  | and don’t know | into programs / software |  |  | made. Scale, efficiency |  |  |  | final deliverable |  | a post report plan |  | submit and
to dealerships |  | can find more to support |  | Discuss strengths and |  | discuss appropriate | [11 empty] | get ready for
|  | our theories / ideas |  | weaknesses of data |  | statistical model | [11 empty] | absolute final review
2 Days |  | 2 Days |  | 2 Days |  | 1 Day | 3 Days |  |  | 4 Days |  |  |  | 2 Days |  | 2 Days |  | 1 Day
Note About Responsibility | [5 empty] | Timeline Notes | [8 empty] | Final Deliverable
We have agreed to split the workload evenly | [5 empty] | Everything is still subject to change due to the nature of this project | [8 empty] | Video, and a report
everyone is expected to do the same amount | [5 empty] | and not knowng how long each step will take / how much time we can
and same kind of work so we are all on the same page | [5 empty] | dedicate a week / a day to working on things.
And are not repeating work. This way we can
create a more cohesive report